## Sheet1
Activities undertaken by WHO_Alliance project
SL# | Date | Duration | Topic | Particinat | Facilitators | Venue
1 | 1.2.2011 | one month | Qualitatative Baseline survey | Policy makers, PM, academicians | PI, Co-PI, Anthropologist | Different places
2 | 1.3.2011 | One hour | Seek permisiion from DG of DGHS | Study team | PI | DGHS
3 | 11.04.2011 | half day | Consulattion meeting to form TAG | Directors, PM, DPM | ADG(Admin) | DGHS
4 | 30.6.2011 | Half day | 1st TAG meeting | TAG members | Director(MIS) | PHSD, icddr,b
5 | 12.6.2011 | Full day | National workshop | Different stake holders | Study team | Spectra convention center, Gulshan
6 | 7-11.8.2011 | 5 days | TOT | Directors, PM, DPM, investigators | Internation consultant | PHSD, icddr,b
7 | 10.10.2011 | Half day | 2nd TAG meeting | TAG members | DIRector(R&P)) | PHSD, icddr,b
8 | 22-24.11.2011 | 3 half day | 1st Executive training | DPM, AD, PM, clinician, field managers | TOT facilitators | PHSD, icddr,b
9 | 13.12.2011 | Half day | Orientation workshop to develop research guideline | Directors, Professors, DPM, PM | Planning and Research unit | MIS conference room, DGHS
10 | 18-20.12.2011 | 3 day | Eveidance based medicine | Professors, asso & assist prof, GPs | PI, study investigators | Shahid Swarawardi Medical College
11 | 16.1.2012 | Half day | Dissemination programme on cell phone based intervention | Directors, PM, DPM, GPS, Academicians | RPCC, P&R unit, DGHS | DG conference room, DGHS
12 | 25.1.2012 | Two hours | Investigators meeting | all investigators | Study team | PHSD, icddr,b
13 | 14-16.2.2012 | Three days | 2nd Executive training | DPM, AD, PM, clinician, field managers | TOT facilitators | PHSD, icddr,b
14 | 11-13.3.2012 | Three days | Consultative workshop to develop executive training manual | Study investigators | Study team | Srimpngol, Moulovi bazzar
15 | 20-22.3.2012 | Three days | 3rd Executive training | Civil surgeon, deputy directors, consultants, FH&FPO, RMO | TOT facilitators | Cox's Bazar, Chittagong
16 | 4-7.4.2012 | Three days | Field travel to conduct quantitative survey | Civil surgeon, Assitant professor, DDFP | PI, study investigator | Khulna
17 | 16.4.2012 | half day | Policy dialogue on Maternal Health Strategy in Bangladesh | Country policy makers, professional bodies, DPs, NGOs | Line Director MNC&AH and PI | ICDDR,B
18 | 23-25.6.2012 | Three days | 4th Executive training | Civil surgeon, deputy directors, consultants, FH&FPO, RMO | TOT facilitators | School Health Clinic, Khulna
19 | 14-16.7.2012 | Three days | 5th Executive training | Civil surgeon, deputy directors, consultants, FH&FPO, RMO | TOT facilitators | Division Director Office, Rajshahi
20 | 6-8.8.2012 | Three days | 6th Executive training | Civil surgeon, deputy directors, consultants, FH&FPO, RMO | TOT facilitators | Meeting Room, RDRS, Rangpur
21 | 3-5.9.2012 | Three days | 7th Executive training | Civil surgeon, deputy directors, consultants, FH&FPO, RMO | TOT facilitators | Celebration Point, Police Line Road in Barisa
22 | 1-19.9.2012 | Three days | 8th Executive training | Civil surgeon, deputy directors, consultants, FH&FPO, RMO | TOT facilitators | MAE Unit, MAG Osmani Medical College in Sylhet